NORTH AMERICAN ISMAILI GAMES 2027 Logistics Weekly Update September 10 - September 16, 2026 190 DAYS TO GAMES; 2 VENUES CONTRACTED; 10 / 102 MILESTONES CLOSED.

Leadership release | Prepared September 16, 2026

Key Progress This Period

The Farmers Branch/Northlake agreement is now countersigned. The $11,500 deposit received internal approval and payment instructions were submitted; settlement confirmation remains open.

UTA received the venue-needs proposal and tentatively identified soccer, cricket, track, flag football, basketball, dance/auditorium and chess capacity. Tennis is unavailable; final availability and pricing remain pending.

Lewisville offered September 22 and 23 planning windows. Rizwan selected September 22 from 1:00 to 2:30 PM, subject to final confirmation.

Leadership aligned on a working F&B assumption of $60 per person per day, Thursday through Sunday, covering athletes and volunteers.

September onsite planning advanced with Northlake and UTA as the current site visits; additional facility photos and videos are still needed.

Venue and Operations Update

Farmers Branch / Northlake and StarCenter

Status: Contracted; payment confirmation open

The DSE agreement has been countersigned.

The contractual deposit is $11,500, and internal site-payment approval is complete.

Payment instructions were submitted through the JMC process; confirmation that the ACH settled has not been received.

Northlake is planned for the September onsite visit, tentatively at 4:00 PM on September 26.

UTA and Outdoor Fields

Status: Promising multi-sport option; commercial details open

UTA is tentatively evaluating 3 soccer fields, 1 cricket field, 1 track, 1 full-size field convertible to flag football or 7v7 soccer, 2 baseball fields as backup configurations, 4 basketball courts, an auditorium and a multipurpose chess room.

Tentative operating window is Thursday for setup and Friday through Sunday for competition.

UTA tennis is unavailable. Exact capacity, pricing, parking impact and contracting terms remain pending.

The UTA onsite-visit time and final availability matrix still need confirmation.

Cricket

Status: Final site model and contract remain open

The current sports assumption requires 5 fields for 22 teams: 14 men’s and 8 women’s teams.

McKinney reported 2 cricket fields available March 25-28. Grand Prairie Stadium is available March 25-27 but not March 28.

Oklahoma City remains an evaluated direction, and UTA may provide 1 additional cricket field.

Kiran was asked to follow up with Abid on the cricket contract. Final field mix, women’s location, pricing and operating plan remain unresolved.

Indoor Sports, Tennis and Pickleball

Status: Recommendation and cost validation required

Badminton and table tennis are leaning toward Northlake/Farmers Branch with third-party operators managing setup, subject to a final Logistics and Sports recommendation.

Pickler Universe remains a likely pickleball option, but the approximately $52,000 discussion requires an itemized invoice, final court count and confirmation of security and porter costs.

Dance-stage capacity and chess-room dimensions at Pickler remain open.

Courts of McKinney cannot supply all requested tennis courts for the full schedule, and UTA tennis is unavailable. The final tennis combination remains at risk.

Hotels, F&B and Transportation

Status: Planning active; baseline decisions still needed

The working F&B budget is $60 per person per day for athletes and volunteers, including breakfast, lunch, dinner, snacks, hydration and service supplies.

The hotel lead is ready to review options. Hotel contracts and the designated hotel webpage are both due October 1 in the PMO plan.

Transportation planning assumes airport-to-registration/hotel loops, hotel-to-major-venue service and secondary links to smaller venues.

Final athlete counts and venue assignments are required before hotel, meal and shuttle volumes can be validated.

Decisions Needed

Confirm that the $11,500 Farmers Branch/Northlake payment has settled. Approve which UTA facilities should advance to pricing and contracting. Finalize the badminton and table-tennis venue/third-party operating model. Select the final tennis and pickleball combination and establish a decision deadline. Confirm the final cricket field mix, women’s location and March 28 coverage. Select the Sunday outdoor-field replacement and weather-contingency facilities. Confirm whether spectator meals and shuttle service are within Logistics scope.

Cross-Vertical Dependencies

Legal: Venue Contracts Executed remains due October 15, 2026; the PMO plan does not name an owner.

Finance: Final budget approval and the payment/reimbursement process were due September 6. Finance requested a soft-budget review with Logistics.

Sports: Final athlete counts, sport schedules and court/field requirements are needed to size venues, hotels, meals and transportation.

Human Resources: The central directory lists only Rizwan and Azmina under Logistics, and the Sub-Team Directory has no Logistics roster entries.

PMO: The master tracker shows all 15 Logistics items as Not Started and assigns every item to Rizwan, despite active work across the PMO team.

Actions: Upcoming Week Plan

Obtain UTA’s final availability matrix, pricing, parking constraints and onsite-visit time.

Confirm the September 22 Lewisville meeting and issue the calendar invitation.

Obtain written confirmation that the StarCenter ACH settled and file the countersigned agreement.

Complete the cricket contract follow-up and publish the recommended field/site scenario.

Finalize the badminton, table-tennis, tennis and pickleball recommendations with Sports.

Schedule the hotel-options review and protect the October 1 hotel-contract/page milestones.

Prepare Logistics soft-budget assumptions for Finance.

Collect photos/videos for facilities not visited during the September onsite.

Update the PMO tracker with actual statuses, owners and cross-functional dependencies.

Add confirmed Logistics personnel and staffing needs to the central HR directories.

Upcoming Coordination

Lewisville planning discussion: September 22, 2026, 1:00-2:30 PM, pending final confirmation

National leadership onsite: September 25-27, 2026

Weekly Site Management meeting: Thursdays, 9:00-9:45 PM CDT

In-person Logistics meeting: October 24-25, 2026; arrivals October 23