NORTH AMERICAN ISMAILI GAMES 2027 Logistics Weekly Update August 31 - September 9, 2026 197 DAYS TO GAMES; 2 VENUES CONTRACTED; 4 / 88 MILESTONES CLOSED.

Leadership release | Prepared September 9, 2026

Key Progress This Period

Farmers Branch/Northlake deposit approvals were completed on September 8 for the contractual amount of $11,500.

Lewisville Parks and Recreation connected the team with the group responsible for sports tournaments, and Rizwan requested an introductory planning call on September 9.

UTA confirmed that its tennis courts are unavailable for the event weekend, provided application paperwork, and continued checking other athletics facilities.

Courts of McKinney confirmed it cannot provide all 12 requested tennis courts for the full schedule. The team requested its actual availability and time slots.

A recurring Logistics Site Management meeting was established for Thursdays from 9:00 to 9:45 PM.

Venue and Operations Update

Farmers Branch / Northlake and StarCenter

Status: Advancing, with final confirmations open

The contract states an $11,500 deposit; NAIG lead approval, and site-payment approval were completed.

Zain was asked to prepare and release the payment, pending confirmation that the funds settled.

The requested DSE countersigned contract has NOT been received.

Cricket

Status: Direction identified; commercial and operating details open

Oklahoma City remains the primary cricket direction.

Three turf-wicket fields are operational, and two additional fields are planned by year-end.

The site currently has no lighting.

Contract, pricing, field-completion timing, and lighting details remain pending.

The stadium was tentatively held for four days at $3,500 per day without lights or $4,000 per day with lights.

The final venue mix, including whether United Cricket Grounds is required, remains undecided.

Women's pitch surface, division allocation, match days, meals, hotels, and umpire arrangements remain open.

Soccer and Outdoor Fields

Status: Coverage gap remains for Sunday

Gateway Park can support Friday and Saturday but not Sunday because of Easter restrictions.

Lewisville engagement moved forward through Stacie Anaya and Marcus, whose team manages sports tournaments in the city park system.

Lewisville was asked to explore 4-5 high-quality grass or turf fields and broader city partnership opportunities.

Rizwan requested a planning call with Lewisville on September 9.

UTA is checking athletics-field availability and warned that baseball or softball events could create parking constraints.

A Sunday replacement and weather-contingency facilities remain unresolved.

Tennis and Pickleball

Status: At risk until a complete venue combination is selected

Courts of McKinney cannot provide all 12 tennis courts for the entire requested period.

The team requested the facility's available courts, specific time slots, pricing, and food policy.

UTA confirmed its tennis courts are unavailable for the event weekend.

UTA supplied its facility application, and Rizwan requested a September 10 call to select the appropriate spaces and options.

The final tennis and pickleball venue combination remains open.

Decisions Needed Confirm whether the $11,500 Farmers Branch/Northlake payment has settled. Obtain and file the DSE countersigned contract. Select the Sunday replacement for Gateway Park. Confirm the final cricket venue model and women's cricket location. Select the tennis and pickleball venue combination. Decide whether Logistics will provide food and shuttle service to spectators. Confirm the Logistics representative for the Command Center.

Cross-Vertical Dependencies Legal: Milestone #14, Venue Contracts Executed, has no named owner and is due October 15, 2026. PMO: Final minute-by-minute and overall program schedule is due February 1, 2027. Human Resources: Final volunteer assignments from every vertical are due February 6, 2027. Command Center: On-site radios must be procured, tested, and ready by March 25, 2027.

Actions:

Upcoming Week Plan

Abid / Cricket team: Obtain OKC pricing, contract, lighting status, and the completion date for the two additional fields.

Cricket team: Publish venue scenarios covering men's and women's assignments, pitch types, competition days, meals, hotels, and pricing.

Site Management: Identify a Sunday soccer replacement and document the weather-contingency plan.

Registration / Legal: Close waiver, health-data, coach/chaperone, and transportation-liability questions.

Select the tennis and pickleball venue combination or set a firm decision deadline.

Confirm whether UTA is viable for outdoor fields or other facilities.

Assign a named Logistics owner to every confirmed venue.

Decide spectator food and shuttle policies.

Confirm Logistics staffing requirements and submit recruiting needs.

Review the new slot and equipment files added to the Logistics Drive.

Upcoming Coordination

Weekly Site Management meeting: Thursdays, 9:00-9:45 PM CDT

National team meeting: September 26-27, 2026

In-person Logistics meeting: October 24-25, 2026